## Slide 1: Pharmacist Thrive Program
Project for Master's in Healthcare Data Analytics
Project Manager: Yong Huang

## Slide 2: Rationale
Burnout affects over 51% of pharmacists (Dee et al., 2022) and worsened post-COVID (NABP, 2024).
Burnout harms pharmacists' mental health and compromises patient safety (Anekwe, 2019).
Pharmacists lack structured peer support systems, unlike physicians, nurses, and lawyers.
Image source: Pharmacy Today (2023)

## Slide 3: Rationale
Pharmacist Thrive Program provides peer-support workshops that complement NABP’s mental health initiative with a cost-effective, structured, and practical solution.
Reduces stress and improves retention, addressing the pharmacist shortage.
Protects patient safety by supporting pharmacist focus and well-being.
Builds on physician peer support successes while adapting for pharmacists' needs (Shapiro & Galowitz, 2016; Pereira et al., 2021).

## Slide 4: Objectives
Provide pharmacists with burnout prevention strategies and coping tools.
Build peer support networks to boost well-being and job satisfaction.
Strengthen workforce retention and enhance patient safety through mental resilience.
Create web-based resources for ongoing support and education.

## Slide 5: Characteristics
Pilot in three cities
Ten-week cycles with meetings every other Saturday
Session 1: Led by a psychologist
Sessions 2–5: Led by trained peer supporters
Week 1​
Psychologist-led
Week 1​
Psychologist-led
Week 9​
Peer supporter-led
Week 7​
Peer supporter-led
Week 5​
Peer supporter-led
Week 3
Peer supporter-led

## Slide 6: Requirements
Human Resources:
Three contracted psychologists for initial sessions.
Six trained peer supporters (two per city) for facilitating discussions.
NABP's existing team for marketing, content, and logistics.

## Slide 7: Requirements
Physical & Digital Infrastructure:
Meeting room spaces for in-person sessions.
Dedicated webpage on NABP.org for sign-ups and resources.
Marketing and outreach materials for program promotion.

## Slide 8: Requirements
Program Implementation & Evaluation:
Participant recruitment via pharmacy outreach and email.
Pre- and post-session surveys for measuring impact.
Ongoing data collection and analysis for program refinement.

## Slide 9: Key Internal Stakeholders
Yong Huang (External PM): Oversaw the project execution and ensured deliverables were met.
Senior Communications Specialist: Led awareness and participant recruitment efforts.
Web Developer: Developed and maintained the program webpage.
Member Engagement Coordinator: Contracted psychologists and developed website content.
Administrative Coordinator: Secured meeting locations and managed logistics.
NABP Chairperson & NABP President: Executive sponsorship

## Slide 10: Key External Stakeholders
Web developer II: Developed the webpage for peer-supporter training course
Instructional designer and psychologist: Designed peer-supporter online training course
Three psychologists: Lead initial sessions
Peer supporters: Volunteer pharmacists who lead discussions.

## Slide 11: Deliverables
Project management-related deliverables: 1. Stakeholder registry 2. Project charter 3. Scope Statement 4. Requirements traceability matrix 5. Work Breakdown Structure (WBS) with schedule, budget, and activity tracking 6. Probability impact matrix

## Slide 12: Deliverables
Product-related deliverables: 1. Burnout prevention workshop sessions: A series of 5 group sessions scheduled every other Saturday over a 10-week cycle. A total of 5 cycles during the first year.
2. A NABP webpage for sign-ups and program details, educational materials and CE content. 3. Flyers, email campaigns and digital promotion through NABP newsletters and social media. 4. Collection of pre- and post- session surveys to assess participant satisfaction and effectiveness in reducing burnout.

## Slide 13: Added Deliverable
An online training course for peer supporters—was added mid-project.
Developed by an instructional designer and a psychologist, and integrated into a standalone training site by a hired web developer.
The addition was made to streamline the training process and reduce the need for multiple live training sessions.

## Slide 14: Success Criteria & Early Results
Success Criteria:
Stress Reduction: Pre- and post-session surveys to measure improvements (too early to assess).
Participant Engagement: Target — 80% session completion.
Positive Feedback: Collect qualitative feedback on well-being, coping strategies, and job satisfaction.
Early Results:
Strong initial sign-ups for first sessions.
Project completed on time and $4,500 under budget

## Slide 15: Schedule
Week 1: Extended planning phase
Week 2: Identified peer supporters; launched marketing & outreach
Weeks 2–3: Developed educational articles, CE session, and registration system
Weeks 4–9: Ongoing marketing, registrant follow-up, and site maintenance

## Slide 16: Schedule
Weeks 5–6: Hired psychologists; finalized session structure
Weeks 6–8: Hired web developer & instructional designer; created online training course
Week 9: Conducted peer supporter training
Week 10: Program sessions launched; project closed

## Slide 17: Budget
Charter estimated budget: $8,760
Baseline (refined) estimate: $32,904.50
Final actual cost: $28,351.87
Main reasons for initial differences:
Charter severely underestimated labor costs (assumed modest stipends).
Baseline recalculated labor using standardized hourly rates ($60/hr, $45/hr, $30/hr).

## Slide 18: Approach
Waterfall methodology
Balanced resources: Combined volunteer peer supporters, targeted psychologist support, and NABP staff resources to ensure cost-effectiveness and impact.
Peer supporters recruited through NABP’s outreach; psychologists hired jointly by PM and NABP team.
Staff handled marketing, web development, content creation, and meeting logistics.

## Slide 19: Changes Made
Scope Changes:
Added an online training course for peer supporters.
Additional responsibilities assigned:
  Website monitoring and maintenance.
  Signup confirmation.
Schedule Changes:
Planning Phase was extended from two to seven days. Other phases were therefore delayed, and some tasks had to start concurrently.

## Slide 20: Changes Made
Budget Changes:
Shifted labor cost calculation method: ➔ From stipend assumption ($1500) to standardized hourly rate by task/deliverable ($22,730).
Refined HR time estimates: ➔ Realized some assigned full-day rates were overestimated due to idle/wait times.
Resource Changes:
Adding the online training course required hiring two additional contractors — a web developer and an instructional designer.

## Slide 21: Weaknesses
Uncertainty in peer supporter performance and participant retention.
Early budgets underestimated and then miscalculated labor costs, reflecting inexperience.

## Slide 22: Areas for future work
Data Analytics:
Develop an evaluation system using survey data, participation metrics, and feedback trends.
Program Expansion:
Scale to additional cities based on Year 1 results.
Continuous Improvement:
Refine peer supporter training based on feedback.
Enhance marketing strategies to improve participant engagement.

## Slide 23: LESSONS LEARNED
Allow More Time for Planning: Early stages often take longer than expected.
Save Multiple Baselines: After major schedule changes, saving new baselines helps accurately track progress and perform meaningful earned value analysis.

## Slide 24: LESSONS LEARNED
Initial charter budget reflected my inexperience as a new project manager.
Future projects: ➔ Budget labor based on hours worked per deliverable, not broad assumptions. ➔ Recognize idle time and waiting periods when assigning costs.
Importance of continuous re-budgeting and reality checks during project execution.

## Slide 25: References
Dee, J., Dhuhaibawi, N., & Hayden, J. C. (2022). A systematic review and pooled prevalence of burnout in pharmacists. International Journal of Clinical Pharmacy, 1–10. https://doi.org/10.1007/s11096-022-01520-6
Shapiro, J., & Galowitz, P. (2016). Peer support for clinicians: A programmatic approach. Academic Medicine, 91(9), 1200-1204. https://doi.org/10.1097/ACM.0000000000001297
Pereira, L., Radovic, T., & Haykal, K. A. (2021). Peer support programs in the fields of medicine and nursing: A systematic search and narrative review. Canadian Medical Education Journal, 12(3), 113–125. https://doi.org/10.36834/cmej.71129
National Association of Boards of Pharmacy (NABP). (2024). Working to support pharmacist mental health and well-being. Retrieved March 14, 2025, from https://nabp.pharmacy/news/blog/working-to-support-pharmacist-mental-health-and-well-being/